## Sprint Plan
FunnelStream Sprint Plan, 4-13 October 2026 (5 members)
ID | Task | Owner | Start | End | Days | Hours | Depends on | Type | Notes | Status
T1 | Scaffold repo, Python env, Docker Compose stack | Member 1 | 2026-10-04 | 2026-10-04 |  | 6 | - | Build | Compose memory limits | Done
T1c | Remove MinIO from stack; local Delta plus Databricks | Member 1 | 2026-10-04 | 2026-10-04 |  | 1 | T1 | Build | Amendment A | Done
T1d | Kafka host listeners, Airflow deps and mounts, env and requirements | Member 1 | 2026-10-05 | 2026-10-05 |  | 2 | T1c | Build | Amendment B | In progress
T0 | Databricks workspace, SQL warehouse, token, one test upload | Member 4 | 2026-10-05 | 2026-10-05 |  | 3 | - | Setup | Human step. Token goes in .env only | To do
T2 | Event contracts and validator | Member 2 | 2026-10-04 | 2026-10-04 |  | 4 | - | Build | Hardened in T6b | Done
T3 | Simulator: customer journeys (funnel, UTM) | Member 1 | 2026-10-05 | 2026-10-06 |  | 8 | T1 | Build | 64-bit ids | Done
T4 | Simulator: orders and delivery lifecycle | Member 1 | 2026-10-06 | 2026-10-07 |  | 8 | T3 | Build | Status rank | Done
T5 | Mock ad API and campaign dataset | Member 4 | 2026-10-05 | 2026-10-05 |  | 4 | T1 | Build | 400 handling, tz | Done
T6 | Kafka topics, idempotent publisher, runner | Member 2 | 2026-10-05 | 2026-10-06 |  | 6 | T2, T4 | Build | History and live modes | Done
T6b | Noise injection and handling primitives | Member 5 | 2026-10-06 | 2026-10-07 |  | 12 | T6 | Build | 16 noise types, manifest | Done
T7 | Spark session and Bronze ingest (3 tables, local Delta) | Member 2 | 2026-10-07 | 2026-10-07 |  | 6 | T6, T1d | Build | Needs Python 3.11, Java 17, winutils | To do
T8 | Silver: validate, dedup, flatten, quarantine, orders table | Member 2 | 2026-10-08 | 2026-10-09 |  | 12 | T7, T6b | Build | Highest-risk Spark task | To do
T9 | Gold builders (Spark reference) and local live metrics | Member 3 | 2026-10-09 | 2026-10-10 |  | 8 | T8 | Build | Production Gold is T10c SQL | To do
T10 | Postgres fallback DDL, Databricks DDL, loader | Member 3 | 2026-10-05 | 2026-10-05 |  | 6 | T1 | Build | Delta types differ | To do
T10b | GoldStore interface, Databricks backend, publish_silver | Member 3 | 2026-10-06 | 2026-10-06 |  | 8 | T10, T0 | Build | Fake-connection tests | To do
T10c | Gold build: MERGE SQL, dims, campaign and date loads | Member 3 | 2026-10-10 | 2026-10-11 |  | 12 | T10b, T8 | Build | Single Gold writer | To do
T11 | SCD2 dimensions (customer, product) | Member 4 | 2026-10-06 | 2026-10-06 |  | 5 | T3, T10b | Build | valid_to 9999-12-31 | To do
T12 | Campaign snapshots and fact_campaign_daily | Member 4 | 2026-10-07 | 2026-10-07 |  | 6 | T5 | Build | 503 retry, quarantine rules | To do
T13 | Attribution (last touch, first touch) | Member 4 | 2026-10-11 | 2026-10-11 |  | 4 | T9 | Build |  | To do
T14 | Recommendations and city-product table | Member 4 | 2026-10-08 | 2026-10-09 |  | 6 | T8 | Build | Distinct sessions | To do
T15 | Batch runner and Airflow DAG (Python fallback) | Member 4 | 2026-10-10 | 2026-10-11 |  | 8 | T10c-T14 | Build | Takes a store, no psycopg | To do
T16 | SQL checks incl. noise manifest check | Member 5 | 2026-10-12 | 2026-10-12 |  | 6 | T10c, T13 | Build | Python check type | To do
T17 | Samples, benchmark, failure demo, README | Member 5 | 2026-10-12 | 2026-10-12 |  | 6 | T8, T10c | Build | Demo reads local Silver | To do
T18 | Power BI model and five pages (Databricks connector) | Member 5 | 2026-10-10 | 2026-10-11 |  | 10 | T10c | Build | Read-only token | To do
T19 | Customer 360 table and page (STRETCH) | Member 4 | 2026-10-12 | 2026-10-12 |  | 4 | T13 | Stretch | Cut first if late | To do
M1 | Integration: Kafka to Silver to Databricks Gold end to end | All | 2026-10-10 | 2026-10-10 |  | 0 | T10c | Integration | Team session | To do
M2 | Failure demo, 1-2M run, benchmark recorded | All | 2026-10-12 | 2026-10-12 |  | 0 | T16, T17 | Integration | Team session | To do
M3 | Rehearsal, final deck and PDF check | All | 2026-10-12 | 2026-10-12 |  | 0 | M2 | Milestone | Share links from Share menu | To do
M4 | Defense | All | 2026-10-13 | 2026-10-13 |  | 0 | M3 | Milestone |  | To do
Assumptions
1. | Productive hours per member per day: 6 (blue input on Team Load sheet).
2. | Hours are focused build time, not calendar time. Integration and milestone rows (owner All) carry no hours and are excluded from Team Load.
3. | Blue text = inputs you can change. Black = formulas.
4. | T19 is stretch: drop it first if the schedule slips. Cut order after that: T16 extras, T18 pages 5 to 6.
5. | Python 3.11 and Java 17 are installed. Status column is an input (blue): Done, In progress, To do.
6. | T0 is a human step: create the Databricks workspace, SQL warehouse and token. Keep the token in .env only.

## Team Load
Team load per member
[6 empty] | Productive hours per day | 6
Member | Tasks | Hours assigned | Capacity (hours) | Load % | Status | Working days (4-12 Oct) | 9
Member 1
Member 2
Member 3
Member 4
Member 5
Team total

## Gantt
Timeline: coloured cells show each task's days (yellow = milestones)
ID | Task | Owner | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13