## Sprint Plan
FunnelStream Sprint Plan, 4-13 October 2026 (5 members)
ID | Task | Owner | Start | End | Days | Hours | Depends on | Type | Notes
T1 | Scaffold repo, Python env, Docker Compose stack | Member 1 | 2026-10-04 | 2026-10-04 |  | 6 | - | Build | Compose memory limits set here
T2 | Event contracts and validator | Member 2 | 2026-10-04 | 2026-10-04 |  | 4 | - | Build | Pure Python, no infra
T3 | Simulator: customer journeys (funnel, UTM) | Member 1 | 2026-10-05 | 2026-10-06 |  | 8 | T1 | Build
T4 | Simulator: orders and delivery lifecycle | Member 1 | 2026-10-06 | 2026-10-07 |  | 8 | T3 | Build | Status rank in streaming/common/status.py
T5 | Mock ad API and campaign dataset | Member 4 | 2026-10-05 | 2026-10-05 |  | 4 | T1 | Build | Feeds T12
T6 | Kafka topics and idempotent publisher | Member 2 | 2026-10-05 | 2026-10-06 |  | 6 | T2, T4 | Build | Route function can start on T2
T7 | Spark session and Bronze ingest | Member 2 | 2026-10-07 | 2026-10-07 |  | 6 | T6 | Build | Needs Java 17
T8 | Silver clean: dedup, late flag, quarantine | Member 2 | 2026-10-08 | 2026-10-09 |  | 10 | T7 | Build | Highest-risk Spark task
T9 | Gold stream tables (orders, lines, funnel, live metrics) | Member 3 | 2026-10-09 | 2026-10-10 |  | 10 | T8 | Build | Single writer: Spark
T10 | Postgres DDL and idempotent Gold loader | Member 3 | 2026-10-05 | 2026-10-05 |  | 6 | T1 | Build | Roles analyst, engineer, admin
T11 | SCD2 dimensions (customer, product) | Member 4 | 2026-10-06 | 2026-10-06 |  | 5 | T3 | Build | Tracked columns per spec
T12 | Campaign snapshots and fact_campaign_daily | Member 4 | 2026-10-07 | 2026-10-07 |  | 6 | T5 | Build | Null-safe ratios
T13 | Attribution (last touch, first touch) | Member 3 | 2026-10-11 | 2026-10-11 |  | 4 | T9 | Build
T14 | Recommendations and city-product table | Member 4 | 2026-10-08 | 2026-10-09 |  | 6 | T8 | Build | Active products only
T15 | Batch runner and Airflow DAG (Python fallback) | Member 4 | 2026-10-10 | 2026-10-11 |  | 8 | T10-T14 | Build | Fallback = same function
T16 | SQL data-quality checks | Member 3 | 2026-10-12 | 2026-10-12 |  | 4 | T9, T13 | Build | Runs after every load
T17 | Samples, benchmark, failure demo script, README | Member 5 | 2026-10-12 | 2026-10-12 |  | 6 | T8, T9 | Build | Failure demo needs T8 checkpoint
T18 | Power BI model and five pages | Member 5 | 2026-10-10 | 2026-10-11 |  | 10 | T9, T10 | Build | Import mode, delivered ROAS headline
T19 | Customer 360 table and page (STRETCH) | Member 4 | 2026-10-12 | 2026-10-12 |  | 4 | T13 | Stretch | Cut first if late
M1 | Integration: Kafka to Silver to Postgres end to end | All | 2026-10-10 | 2026-10-10 |  | 0 | T9 | Integration | Team session
M2 | Failure demo, 1-2M run, benchmark recorded | All | 2026-10-12 | 2026-10-12 |  | 0 | T16, T17 | Integration | Team session
M3 | Rehearsal, final deck and PDF check | All | 2026-10-12 | 2026-10-12 |  | 0 | M2 | Milestone | Share links from Share menu
M4 | Defense | All | 2026-10-13 | 2026-10-13 |  | 0 | M3 | Milestone
Assumptions
1. | Productive hours per member per day: 6 (blue input on Team Load sheet).
2. | Hours are focused build time, not calendar time. Integration and milestone rows (owner All) carry no hours and are excluded from Team Load.
3. | Blue text = inputs you can change. Black = formulas.
4. | T19 is stretch: drop it first if the schedule slips.
5. | Python 3.11 and Java 17 must be installed before T1 and T7.

## Team Load
Team load per member
[6 empty] | Productive hours per day | 6
Member | Tasks | Hours assigned | Capacity (hours) | Load % | Status | Working days (4-12 Oct) | 9
Member 1
Member 2
Member 3
Member 4
Member 5
Team total

## Gantt
Timeline: coloured cells show each task's days (yellow = milestones)
ID | Task | Owner | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13