## Sprint Plan
FunnelStream Sprint Plan, 4-13 October 2026 (5 members)
Status as of Thursday 8 October 2026. Dates of Done tasks are actual (commit history); dates of open tasks are planned.
ID | Task | Owner | Start | End | Days | Hours | Depends on | Type | Notes | Status
T1 | Scaffold repo, Python env, Docker Compose stack | Member 1 | 2026-10-04 | 2026-10-04 |  | 6 | - | Build | Compose memory limits | Done
T1c | Remove MinIO from stack; local Delta plus Databricks hybrid | Member 1 | 2026-10-04 | 2026-10-04 |  | 1 | T1 | Build | Amendment A | Done
T1d | Kafka host listeners, Airflow deps and mounts, env names | Member 1 | 2026-10-04 | 2026-10-04 |  | 2 | T1c | Build | Amendment B | Done
T0 | Databricks workspace, SQL warehouse, token, one upload test | Member 4 | 2026-10-05 | 2026-10-05 |  | 3 | - | Setup | Human step. Token goes in .env only | Done
T2 | Event contracts and validator | Member 2 | 2026-10-04 | 2026-10-04 |  | 4 | - | Build | Hardened in T6b | Done
T3 | Simulator: customer journeys (funnel, UTM) | Member 1 | 2026-10-04 | 2026-10-04 |  | 8 | T1 | Build | 64-bit ids | Done
T4 | Simulator: orders and delivery lifecycle | Member 1 | 2026-10-04 | 2026-10-04 |  | 8 | T3 | Build | Status rank | Done
T5 | Mock ad API and campaign dataset | Member 4 | 2026-10-04 | 2026-10-04 |  | 4 | T1 | Build | 400 handling, tz | Done
T6 | Kafka topics, idempotent publisher, runner | Member 2 | 2026-10-04 | 2026-10-04 |  | 6 | T2, T4 | Build | History and live modes | Done
T6b | Noise injection and handling primitives | Member 5 | 2026-10-04 | 2026-10-04 |  | 12 | T6 | Build | Noise kinds with manifest counts (19 after D1) | Done
T7 | Spark session and Bronze ingest (3 tables, local Delta) | Member 2 | 2026-10-04 | 2026-10-04 |  | 6 | T6, T1d | Build | Spark runs in Docker (no winutils) | Done
T8 | Silver: validate, dedup, flatten, quarantine, orders | Member 2 | 2026-10-04 | 2026-10-04 |  | 12 | T7, T6b | Build | Highest-risk Spark task; partitioned by event_date | Done
T9 | Gold builders (Spark reference) and local live metrics | Member 3 | 2026-10-04 | 2026-10-04 |  | 8 | T8 | Build | Reference for the Gold SQL parity tests | Done
T10 | Postgres fallback DDL, Databricks DDL, loader | Member 3 | 2026-10-04 | 2026-10-04 |  | 6 | T1 | Build | One table spec generates both DDL files | Done
T10b | GoldStore interface, Databricks backend, publish_silver | Member 3 | 2026-10-05 | 2026-10-05 |  | 8 | T10, T0 | Build | Verified on the real workspace | Done
C1 | Amendment C: order_returned, COD rule, platform, DLQ removed | Member 1 | 2026-10-05 | 2026-10-05 |  | 4 | T10b | Build | External review items 5, 6, 7, 9, 15, 22 | Done
C2 | Amendment C: Silver platform, returned status, platform conversions | Member 2 | 2026-10-05 | 2026-10-05 |  | 4 | C1 | Build | Silver mirror columns and publish allow-list | Done
C3 | Amendment C: Gold model renames, unknown members (-1), new columns | Member 3 | 2026-10-05 | 2026-10-05 |  | 6 | C2 | Build | agg_/rec_ names, BY DEFAULT identity keys; items 1, 2, 10, 12, 13 | Done
C4 | Cleanup of C1-C3 findings and Databricks migration check | Member 3 | 2026-10-05 | 2026-10-05 |  | 3 | C3 | Build | Real workspace verified read-only | Done
T10c | Gold build: incremental MERGE SQL, dims, dim_date, facts, summaries | Member 3 | 2026-10-06 | 2026-10-06 |  | 12 | T10b, T8 | Build | Real run: 0 mismatches vs reference; single Gold writer | Done
T11 | SCD2 dimensions (customer, product) | Member 4 | 2026-10-06 | 2026-10-06 |  | 5 | T3, T10b | Build | Delivered inside the T10c SQL; one version per day | Done
AD | Yesterday's ad report: batch.ads_report and Airflow DAG | Member 4 | 2026-10-06 | 2026-10-06 |  | 5 | T5, T10b | Build | Pulls once per day, same-day rerun returns the stored report | Done
D1 | District hierarchy, page_url with UTM, dirty_district and dirty_utm noise | Member 1 | 2026-10-06 | 2026-10-06 |  | 5 | T3, T6b | Build | 36 official districts under 7 cities | Done
D2 | district, utm_medium, page_url through Silver, Gold model, DDL | Member 2 | 2026-10-06 | 2026-10-06 |  | 5 | D1, C3 | Build | Real workspace recreated and republished | Done
DEMO | Live demo tooling: --show, universe seed, watch_demo and stop_demo | Member 5 | 2026-10-08 | 2026-10-08 |  | 4 | T6, T7, T8 | Build | Four windows: Kafka, Bronze, Silver, generator | Done
G1 | Live and health tables in Postgres, combined Bronze+Silver job | Member 2 | 2026-10-08 | 2026-10-08 |  | 8 | C3, T8 | Build | Review fixes done; full Docker suite re-run pending | Done
G2 | Grafana in Compose: dashboard, 3 alert rules, alert sink | Member 5 | 2026-10-08 | 2026-10-08 |  | 6 | G1 | Build | Live check: 14 panels, all rules fired | Done
T13 | Attribution (last touch, first touch) as Gold SQL step | Member 4 | 2026-10-08 | 2026-10-08 |  | 4 | T10c | Build | Real run 0 mismatches; 4 Spark tests in a fix round | In progress
T12 | agg_campaign_daily: CPA, cost per delivered order, rates | Member 4 | 2026-10-09 | 2026-10-10 |  | 6 | T13, AD | Build | Last touch; platform conversions beside orders | To do
T14 | agg_city_product_daily (rec_product is cut first) | Member 4 | 2026-10-10 | 2026-10-10 |  | 4 | T10c | Build | Distinct sessions | To do
T15 | Batch runner script: publish, Gold build, checks | Member 4 | 2026-10-10 | 2026-10-11 |  | 6 | T12, T14 | Build | Python is primary; DAG for ad report exists | To do
T16 | SQL checks: the five most important plus manifest check | Member 5 | 2026-10-10 | 2026-10-11 |  | 6 | T10c, T13 | Build | Fail blocks the Power BI refresh | To do
G3 | Failure demo with Grafana: kill Silver, alert, restart, no duplicates | Member 5 | 2026-10-11 | 2026-10-11 |  | 4 | G2, T16 | Build | Best live moment for the defense | To do
T17 | Samples, benchmark, README | Member 5 | 2026-10-11 | 2026-10-12 |  | 6 | T8, T10c | Build | Run 1-2M events once | To do
T18 | Power BI model and pages (Campaign and Funnel first) | Member 1 | 2026-10-11 | 2026-10-12 |  | 10 | T10c, T12 | Build | Read-only token; extra pages only if time | To do
T19 | Customer 360 table and page (STRETCH) | Member 4 | 2026-10-12 | 2026-10-12 |  | 4 | T13 | Stretch | Cut first if late | To do
DOC | Refresh PDF, deck, README screenshots | Member 5 | 2026-10-12 | 2026-10-12 |  | 6 | G3, T18 | Build | Documents are still from 5 Oct | To do
M1 | Integration: Kafka to Silver to Postgres/Grafana and Databricks Gold | All | 2026-10-08 | 2026-10-08 |  | 0 | T10c, G1 | Integration | Verified live on 8 Oct | Done
M2 | Failure demo, 1-2M run, benchmark recorded | All | 2026-10-12 | 2026-10-12 |  | 0 | G3, T17 | Integration | Team session | To do
M3 | Rehearsal, final deck and PDF check | All | 2026-10-12 | 2026-10-12 |  | 0 | M2, DOC | Milestone | Share links from Share menu | To do
M4 | Defense | All | 2026-10-13 | 2026-10-13 |  | 0 | M3 | Milestone |  | To do
Assumptions
1. | Productive hours per member per day: 6 (blue input on Team Load sheet).
2. | Hours are focused build time, not calendar time. Hours of Done tasks are the original estimates, not measured time. Integration and milestone rows (owner All) carry no hours and are excluded from Team Load.
3. | Blue text = inputs you can change. Black = formulas.
4. | T19 is stretch: drop it first. Cut order after that: rec_product and customer_360, the SQL checks beyond the five key ones, Power BI pages beyond Campaign and Funnel. Never cut: attribution (T13), campaign summaries (T12), Grafana (G2) and the failure demo (G3).
5. | Spark runs in Docker (Python 3.11 and Java 17 are inside the image); the host needs Python 3.11 only. Status column is an input (blue): Done, In progress, To do.
6. | T0 was a human step: Databricks workspace, SQL warehouse and token. The token stays in .env only.
7. | Decision date 10 Oct: batch entry point is a Python script (T15). The Airflow DAG exists for the daily ad report only.
8. | Tasks C1-C4, AD, D1, D2, DEMO, G1, G2 were added after the 4 Oct plan (external review, address and tracking URL, live monitoring).

## Team Load
Team load per member
[6 empty] | Productive hours per day | 6
Member | Tasks | Hours assigned | Capacity (hours) | Load % | Status | Working days (4-12 Oct) | 9
Member 1
Member 2 | [5 empty] | Progress (all rows of Sprint Plan)
Member 3 | [5 empty] | Tasks Done
Member 4 | [5 empty] | Tasks In progress
Member 5 | [5 empty] | Tasks To do
Team total | [5 empty] | Hours Done
Hours total
Hours Done %

## Gantt
Timeline: coloured cells show each task's days (yellow = milestones)
ID | Task | Owner | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13